## PD-CR
Child Call ID | Parent call ID | Testing Environment | Category | In Scope | Automation Scope | Issue Description | Priority | UAT SPOC | UAT release date | UAT Completion date (Tentative) | UAT completion date (Actual) | UAT Sign off Date (Tentative) | UAT Sign off Date (Actual) | Calls Ageing | Calls Ageing Bucket | Ageing Bucket | Current Jira Status | vlookup | Comparison | Responsible SPOC | Responsible | Application owner | Date Assigned to current owner | Ageing with current owner | Status Ageing Bucket | Latest Update- UAT | Open defects
Team
OPS-16290 |  |  | NR-CR |  |  | Modification in SR flow for FRAR cases for NGIN policies |  | Ketan Gujar | 2024-10-08 |  |  |  |  | 696 | >21 Days | Over 151 days | Pre-Prod Show Stopper | PAS.JayendraJain | TRUE | PAS.JayendraJain | PAS | Siddharth Godbole | 2026-02-27 | 189 | >21 Days
AP-29 |  |  | CR | Claims |  | Premium will be refunded to claimant under void decision. | High | Ranjit Gaikwad | 2024-10-14 |  |  |  |  | 690 | >21 Days | Over 151 days | UAT Defect Fixing in Progress | Mukesh Bhatt | TRUE | Mukesh Bhatt | PAS | Siddharth Godbole | 2025-04-23 | 499 | >21 Days | Underdefect | AP-1470, 1486,1756,
OPS-18236 |  |  | CR |  |  | FRAR occupation Changes | Medium | Ganesh Pawar | 2024-10-14 |  |  |  |  | 690 | >21 Days | Over 151 days | Pre-Prod Show Stopper | PAS.JayendraJain | TRUE | PAS.JayendraJain | PAS | Siddharth Godbole | 2026-01-13 | 234 | >21 Days | Parent call in pending showstopper | OPS-20675
OPS-17956 |  |  | CR |  |  | PD 215 - Digital revival cases wrongly assign to DOH instead of processing or assign to UW (NGIN Polices) |  | Amit Shende | 2024-12-24 |  |  |  |  | 619 | >21 Days | Over 151 days | UAT-Show Stopper | Sampa.Dey | TRUE | Sampa.Dey | LACP | Soniel | 2026-08-03 | 32 | 0-10 Days | Open defects to be resolved, PDT-17956, Prasad Pai(Balic IT) has requested CRT to provide fresh call revisiting the development required and carryout development in LACP with clean, freshcode base as per mail dated 7th May 266 | OPS-19047, 19051,19052 child calls - Defects - OPS-23998 , 30544 , 33381,33610,33766,34330 pending to be resolved
AP-2091 |  |  | CR | NB |  | Changes at NGIN side for consuming Omnidocs upload/download service | Medium | Ranjit Gaikwad | 2025-02-10 |  |  |  |  | 571 | >21 Days | Over 151 days | UAT Defect Fixing in Progress | Sanket Vijayrane/Pune HO/Technology (512000)/Life | TRUE | Sanket Vijayrane/Pune HO/Technology (512000)/Life | Omni | Soniel | 2025-07-18 | 413 | >21 Days | Issue in Newgen Jar file, awaiting confirmation since may 25 and escalated to Analytics PMO for call closure as no response received since may 25 | AP-2766
AN-1150 |  |  | CR |  |  | NGIN: Payload/API |  | Ankita Machhindranath Pawar | 2025-06-26 |  | 2025-07-07 |  |  | 11 | 11-20 Days | 9-15 days | On Hold |  | FALSE | Nikhilesh.Sundaresan | Analytics | Nikhilesh S | 2025-12-01 | 277 | >21 Days | Super woman not released in NGIN
AN-1100 |  |  | CR |  |  | Superwoman term flag to be passed in EDC API |  | Ankita Machhindranath Pawar | 2025-06-26 |  | 2025-07-07 |  |  | 11 | 11-20 Days | 9-15 days | On Hold |  | FALSE | Kush.Maheshwari | DIGI | Prakash Swain | 2026-01-21 | 226 | >21 Days | Super woman not released in NGIN
AP-1466 |  |  | CR |  |  | NGIN- Dashboard access for updating Pay mode vendor |  | Amit Shende | 2025-07-07 |  |  |  |  | 424 | >21 Days | Over 151 days | UAT Defect Fixing in Progress | Shekhar Khedkar | FALSE | KUNTAL SARKAR | CRT | Saurabh Mishra | 2026-08-09 | 26 | >21 Days | OPen CR pending | CR-AP-5381
AP-1813 |  |  | BAU CR | Claims |  | The death claims, except the cases where investigation is required, should be settled within 15 days of initiating the claim. In death claims where investigation is required, the settlement should be done within 45 days of intimation of the claim. |  | Ranjit Gaikwad | 2025-07-22 |  |  |  |  | 409 | >21 Days | Over 151 days | UAT Defect Fixing in Progress | balic_finance_agilicprojects | FALSE | Sagar gupta | PAS | Siddharth Godbole | 2026-07-16 | 50 | 11-20 Days | Open defects to be resolved. All policies are moving to Investigative. As per Ramesh Santhanagopal’s comment on defect system is calling claims model api to get the risk of the policy. Analytics team check Defect AP-5516. | AP-5527,5528
ITP-3314 |  |  | CR |  |  | NGIN-2024 Regulatory Changes- Modification in AWG_NON-PAS |  | Jayaraman S | 2025-07-22 |  | 2026-01-07 |  |  | 169 | >21 Days | Over 151 days | Actual cost Closure |  | FALSE | Chayan Bhattacharya | PMO | #N/A | 2026-04-15 | 142 | >21 Days
AG-5937 |  |  | CR |  |  | TO enable BH receipting for OPUS/NGIN on DigiAgency. |  | Pranit Sasane/Chaitanya Shashank Kulkarni | 2025-08-21 | 2026-01-28 | 2026-06-23 |  |  | 306 | >21 Days | Over 151 days | Actual cost Closure |  | FALSE | Chayan Bhattacharya | PMO | #N/A | 2026-07-21 | 45 | 0-10 Days | Shared
AN-1109 |  |  | CR |  |  | PASA auto-issuance restriction in suspected CP case |  | Chaitanya Shashank Kulkarni | 2025-10-24 |  | 2025-11-11 |  |  | 18 | 11-20 Days | 16-30 days | Actual cost Closure |  |  | Chayan Bhattacharya | PMO | #N/A | 2026-04-09 | 148 | >21 Days
AP-1845 |  |  | BAU CR |  |  | NAV Allocation of ULIP autopayment cases basis the Receipt date and time (NGIN) Referecne Call -OPS 13023 |  | Rameshwar Yadav/Harshal chougle | 2025-10-30 | 2026-01-31 | 2025-11-14 |  |  | 15 | 11-20 Days | 9-15 days | Regression in Progress | Nikesh Maske | TRUE | Nikesh Maske | UAT | Rohan | 2026-09-01 | 3 | 0-10 Days | Awaiting signoff from CRT deeksha since 15 may 26
OPS-19499 |  |  | CR |  |  | Instigated Surrender API call for NGIN policies on surrender request- LMS Changes |  | Ketan Gujar | 2025-11-14 |  |  |  |  | 294 | >21 Days | Over 151 days | ON HOLD (FROM Pre-Prod) | PAS.KshitizSrivastava | TRUE | PAS.KshitizSrivastava | PAS | Siddharth Godbole | 2026-03-30 | 158 | >21 Days |  | OPS-27414
AN-1198 |  |  | CR |  |  | OCR Analytics layer to be enabled in buy journey to validate documents and auto-issue. |  | Chaitanya Shashank Kulkarni | 2025-11-25 |  | 2026-02-02 |  |  | 69 | >21 Days | 61-90 days | Actual cost Closure | Chayan Bhattacharya | TRUE | Chayan Bhattacharya | PMO | #N/A | 2026-04-09 | 148 | >21 Days |  | AN-1590
AP-3614 | AP-2050 |  | CR |  |  | Automatic" Transfer Portfolio strategy to be handled as "Auto" Transfer Portfolio strategy so that it can consumed by NGIN as it it done for other product |  | omkar jadhav01 | 2025-11-27 |  |  |  |  | 281 | >21 Days | Over 151 days | On Hold (From UAT) | Sanket Vijayrane/Pune HO/Technology (512000)/Life | TRUE | Sanket Vijayrane/Pune HO/Technology (512000)/Life | Omni | Soniel | 2026-07-13 | 53 | 11-20 Days | Product call
AP-3603 |  |  | CR |  |  | "Automatic" Transfer Portfolio strategy to be handled as "Auto" Transfer Portfolio strategy so that it can consumed by NGIN as it it done for other product. |  | Rutuja Dedge | 2025-12-08 |  |  |  |  | 270 | >21 Days | Over 151 days | UAT Defect Fixing in Progress | Venkatesh Sandal G | FALSE | Sanket Vijayrane/Pune HO/Technology (512000)/Life | Omni | Soniel | 2025-12-31 | 247 | >21 Days | On hold due to AP-3614, pending with PMO | AP-3614
OPS-21927 |  |  | NR-CR |  |  | Additional Fields in Instigated Surrender for NGIN policies in CRM | Medium | Ketan Gujar | 2025-12-08 |  |  |  |  | 270 | >21 Days | Over 151 days | Pre-Prod Show Stopper | PAS.KshitizSrivastava | TRUE | PAS.KshitizSrivastava | PAS | Siddharth Godbole | 2026-03-31 | 157 | >21 Days | Awaiting resolution from Infy | ops-27292, ops-23689
OPS-19174 |  |  | CR |  |  | Instigated Surrender API call for NGIN policies on surrender request |  | Ketan Gujar | 2025-12-08 |  |  |  |  | 270 | >21 Days | Over 151 days | Pre-Prod Show Stopper | PAS.KshitizSrivastava | TRUE | PAS.KshitizSrivastava | PAS | Siddharth Godbole | 2026-02-25 | 191 | >21 Days |  | Child call-20130,20131, defect OPS-27414,31088
OPS-20132 |  |  | CR |  |  | Instigated Surrender API call for NGIN policies on surrender request-Ismart |  | Ketan Gujar | 2025-12-09 |  |  |  |  | 269 | >21 Days | Over 151 days | ON HOLD (FROM Pre-Prod) | PAS.KshitizSrivastava | TRUE | PAS.KshitizSrivastava | PAS | Siddharth Godbole | 2026-03-31 | 157 | >21 Days |  | Child call-20130,20131, defect OPS-27414,31088
OPS-20131 |  |  | CR |  |  | Instigated Surrender API call for NGIN policies on surrender request- Iahead Frontend Changes |  | Ketan Gujar | 2025-12-09 |  |  |  |  | 269 | >21 Days | Over 151 days | ON HOLD (FROM Pre-Prod) | PAS.KshitizSrivastava | TRUE | PAS.KshitizSrivastava | PAS | Siddharth Godbole | 2026-03-31 | 157 | >21 Days |  | Child call-20130,20131, defect OPS-27414,31088
AP-1469 |  |  | BAU CR |  |  | NGIN-Modifications to existing unclaimed system configurations in line with IRDAI guidelines |  | Abhijay Pawar | 2025-12-11 |  | 2025-12-16 |  |  | 5 | 0-10 Days | 2-5 days | Regression in Progress |  | FALSE | Mukesh Bhatt | PAS | Siddharth Godbole | 2026-05-18 | 109 | >21 Days | UAT team to proceed with testing on UAT 2 environment. Unclear batch is not available in UAT 2 and require development
AP-2551 |  |  | CR |  |  | Income waiver basis EPFO, Vahan, GSTN -NGIN |  | chaitanya shashank kulkarni | 2025-12-22 | 2026-09-03 | 2026-02-02 | 2026-09-03 | 2026-09-04 | 42 | >21 Days | 31-60 days | UAT In progress |  | FALSE | chaitanya shashank kulkarni | UAT | Rohan | 2026-07-21 | 45 | 0-10 Days |  | AP-5525,AP-5534
PD-1741 |  |  | Production Defect |  |  | Failed to Push data to NGIN at the Digi Journey Error due to Special char in address filed |  | Aditya Kumar | 2026-01-02 |  | 2026-01-02 |  |  | 0 | >21 Days | 0-1 days | Business Approval/Sign off |  | FALSE | Hemlata Pardeshi PMO | PS PMO | Nitin Jaigude | 2026-07-23 | 43 | 0-10 Days | Awaiting signoff since 10 Jun 26
AP-1471 |  |  | CR |  |  | Instant Payment through API in Ngin |  | Abhijay Pawar | 2026-01-06 | 2026-08-26 |  | 2026-08-31 |  | 241 | >21 Days | Over 151 days | UAT Defect Fixing in Progress | balic_finance_agilicprojects | FALSE | Shubham Kishor Patil | UAT | Rohan | 2026-03-10 | 178 | >21 Days | required details of the company’s business account type along with its dimensions.
AG-4850 |  |  | CR |  |  | New Club wise Commission - for IT dev wef 01 Jan 2025 Changes in commission payment structure. - PMACs |  | Nilesh Sawant | 2026-01-07 |  | 2026-06-25 |  |  | 169 | >21 Days | Over 151 days | Pre-Prod In Progress |  | FALSE | balic_finance_agilicprojects | PAS | Siddharth Godbole | 2026-07-23 | 43 | 10-20 Days | Ok received for commission from Sachin Y on 23 Jul 26, UAT signoff pending from finance perspective | AG-7628
OPS-19047 | OPS-17956 |  | CR |  |  | Process Flow Change in CRM - Digital revival cases wrongly assign to DOH instead of processing or assign to UW (NGIN Polices) |  | Amit Shende | 2026-01-12 | 2026-09-10 |  | 2026-09-12 |  | 235 | >21 Days | Over 151 days | UAT-Show Stopper | Kartik Prabhakar Pandit | FALSE | Sagar gupta | PAS | Siddharth Godbole | 2026-06-01 | 95 | >21 Days | Open defects to be resolved | OPS-17956, 19051,19052 child calls - Defects - OPS-23998 , 30544 , 33381, 33547pending to be resolved
FIN-5197 |  |  | CR |  |  | SBI OTC collections - OSB related development and integration required |  | Abhijay Pawar | 2026-01-16 |  | 2026-08-31 |  |  | 227 | >21 Days | Over 151 days | Pre-Prod In Progress |  | FALSE | Sneha.Shirole | Finance | Aditya Hebbar | 2026-07-23 | 43 | 0-10 Days | it is not feasible to use same GL code. Unique GL code will be required to proceed. Required call for discussion with business team. Pending with ITRS and dev team. Call to be tracked under FIN-5197,Required field details should be displayed correct
OPS-28405 |  |  | CR |  |  | Frequency change process enhancement for NGIN and OPUS policies |  | Nikesh Maske | 2026-02-11 |  |  |  |  | 205 | >21 Days | Over 151 days | Testing Showstopper | Sanket Telang | TRUE | Sanket Telang | AGILIC PMO | Vikesh S | 2026-06-12 | 84 | >21 Days | Open defects to be resolved | OPS-33604, 33461, 34164,33645
ITP-4654 |  |  | CR |  |  | NRI flag value need to be built in LACP. |  | Amit Shende | 2026-02-19 |  | 2026-03-09 |  |  | 18 | 11-20 Days | 16-30 days | Actual cost Closure |  | FALSE | Chayan Bhattacharya | PMO | #N/A | 2026-04-08 | 149 | >21 Days | Being tested by Business user | ITP-5191, 5269
ITP-5037 |  |  | CR |  |  | DM related changes PASA |  | Sandip Subhash Darade | 2026-02-24 |  | 2026-02-26 |  |  | 2 | 0-10 Days | 2-5 days | Actual cost Closure |  |  | Chayan Bhattacharya | PMO | #N/A | 2026-04-27 | 130 | >21 Days
OPS-28848 |  |  | BAU CR |  |  | Medical grid development |  | Vidhya C | 2026-02-24 |  |  |  |  | 192 | >21 Days | Over 151 days | Testing Showstopper | Prakash Pongiannan | FALSE | Vidhya.C | UAT | Rohan | 2026-06-08 | 88 | >21 Days | Linked defect PDT-19852 to be resolved | Linked defect PDT-19852
ITP-3403 |  |  | CR |  |  | CKYC Related Changes |  | Sandip Subhash Darade | 2026-03-02 |  | 2026-04-10 |  |  | 39 | >21 Days | 31-60 days | Actual cost Closure |  |  | Chayan Bhattacharya | PMO | #N/A | 2026-06-30 | 66 | >21 Days | Chayan added signoff comment and moved this call ahead
AG-6646 |  |  | CR |  |  | To pass the Agent's club status to NGIN & I-one from source table |  | Rutuja Dedge | 2026-03-09 |  |  |  |  | 179 | >21 Days | Over 151 days | Testing Showstopper | Veera G | FALSE | Mukesh Bhatt | PAS | Siddharth Godbole | 2026-07-21 | 45 | 0-10 Days | Sent for signoff on 19 may 26. 1 term case to be tested. Agent mapping is not available in NGIN and to proceed testing post mapping by PMACS | AG-8079
AP-2427 |  |  | BAU CR |  |  | Development of Form 60 requirements in NGIN/OPUS. |  | Abhijay Pawar | 2026-03-17 | 2026-08-26 |  | 2026-08-31 |  | 171 | >21 Days | Over 151 days | UAT In progress | Ankita Anjali | FALSE | Rohan Deokate | UAT | Rohan | 2026-06-23 | 73 | >21 Days | Awaiting confirmation on digi /NGIN changes to be done
OPS-28402 |  |  | CR |  |  | Employee Temp. Deputation Process & DCB Revoke under NGIN Cashier |  | Pranit Sasane | 2026-03-19 |  | 2026-03-20 |  |  | 1 | 0-10 Days | 0-1 days | Actual cost Closure |  | FALSE | Chayan Bhattacharya | PMO | #N/A | 2026-05-22 | 105 | >21 Days
PD-1952 |  |  | Production Defect |  |  | Accrual event is getting triggered twice in PMACS which leading for duplicate commission for single premium |  | Abhijay Pawar | 2026-03-21 |  |  |  |  | 167 | >21 Days | Over 151 days | UAT TL Review | Harshal Chougule | TRUE | Harshal Chougule | UAT | Rohan | 2026-09-02 | 2 | 0-10 Days | Pending with Amitabh, Policy is getting error out in PMACS with error "Originating event for reversal not found" - This call is also related to single premium finance to check and provide required product for single premium also.
@Sunil Dafade to provide working screenshots for the same
For CDA case We need to do cashiering
Sunil D
ITP-4379 |  |  | CR |  |  | Payment Mode changes at CRM side due to NGIN Upgrade 4.0.0 |  | Sunil Bhalerao | 2026-04-03 | 2026-04-07 | 2026-04-07 |  |  | 4 | 0-10 Days | 2-5 days | Actual cost Closure | Chayan Bhattacharya |  | Chayan Bhattacharya | PMO | #N/A | 2026-04-09 | 148 | >21 Days | As per the confirmation recieved from Pravin wani ,we have to closed this call.
FIN-4673 |  | Preprod | CR |  |  | Cheque clearance status updation of Non-tech CDA without representation |  | Balic finance agilic projects | 2026-04-06 |  |  |  |  | 151 | >21 Days | Over 151 days | Testing Showstopper | BALIC_SIT_Life | TRUE | BALIC_SIT_Life | BALIC_SIT_Life | dba2 | 2026-09-02 | 2 | 0-10 Days | OPen defects to be resolved | FIN-6115
PD-2104 |  |  | Production Defect |  |  | Pending-Premium Case not moved to ACTIVE (Cheque in transit status) |  | Harshal Chougule | 2026-04-07 |  | 2026-07-31 |  |  | 115 | >21 Days | 91-120 days | Business Approval/Sign off | balic_finance_agilicprojects | FALSE | Venkatesh Sandal G | UAT | Rohan | 2026-07-31 | 35 | 0-10 Days | Awaiting for signoff since 18 Jun 26
FIN-5931 |  | Preprod | BAU CR |  |  | Duplicate entries created in NGIN during NEFT Fallout upload |  | Abhijay Pawar | 2026-04-17 |  | 2026-05-11 |  |  | 1 | 0-10 Days | 0-1 days | Testing Showstopper | balic_finance_agilicprojects | TRUE | balic_finance_agilicprojects | PAS | Siddharth Godbole | 2026-07-01 | 65 | >21 Days | OPen defects to be resolved | FIN-6429
OPS-29187 |  |  | BAU CR |  |  | NGIN-PS Changes- Physical NACH registration |  | Sunil Bhalerao | 2026-04-24 | 2026-09-10 |  | 2026-09-14 |  | 133 | 0-10 Days | 121-150 days | Testing Showstopper | nagarjuna chittiboina | TRUE | nagarjuna chittiboina | Balic IT | #N/A | 2026-09-03 | 1 | >21 Days | Signoff received on 7th may 26 and mandate to be registered via journey touch point for final signoff as per SME. Awaiting clarification from BAlic IT
AP-2232 |  |  | CR |  |  | Defense Channel implementation on NGIN |  | Sandip Subhash Darade | 2026-05-01 | 2026-09-02 |  | 2026-09-04 |  | 126 | >21 Days | 121-150 days | Regression in Progress | Sandip Subhash Darade | TRUE | Sandip Subhash Darade | UAT | Rohan | 2026-07-06 | 60 | >21 Days | Shared for Signoff to Meenakshi and Aditya on 9th June | AP-5522, AP-5532, AP-5533
BD-2364 |  |  | CR |  |  | Onboard Defense on NGIN platform |  | Sandip Subhash Darade | 2026-05-01 | 2026-09-02 |  | 2026-09-04 |  | 126 | >21 Days | 121-150 days | Testing Showstopper | Mukesh Bhatt | TRUE | Mukesh Bhatt | PAS | Siddharth Godbole | 2026-07-06 | 60 | >21 Days | Shared for Signoff to Meenakshi and Aditya on 9th June | AP-5522, AP-5532, AP-5533
FIN-4577 |  | Preprod | CR |  |  | PMCAS Accounting date should be aligned with NGIN transaction date |  | Abhijay Pawar | 2026-05-04 | 2026-08-26 |  | 2026-08-31 |  | 123 | >21 Days | 121-150 days | Testing Showstopper | Vaibhav Gaonkar | TRUE | Vaibhav Gaonkar | PAS | Siddharth Godbole | 2026-07-24 | 42 | 11-20 Days | Posted date to change to 03 aug 26 and to restart preprod pending with Anil | FIN-6278, 6727, 6270 & 6863
FIN-4165 |  | Preprod | CR |  |  | IB Scale up - Upload functionality for IB commission invoices not available for GST payout. Currently there is only functionality to update the GST break-up invoice by invoice in PMACS for GST refund accounting and payout |  | Abhijay Pawar | 2026-05-04 | 2026-08-26 |  | 2026-08-31 |  | 114 | >21 Days | 91-120 days | Pre-Prod In Progress | Abhijay.Pawar01 | FALSE | balic_finance_agilicprojects | PAS | Siddharth Godbole | 2026-08-05 | 30 | 0-10 Days
LCF-966 |  |  | CR |  |  | Content correction required on proposal form and policy schedule copy |  | Sandip Subhash Darade | 2026-05-05 |  | 2026-07-13 |  | 2026-07-13 | 69 | >21 Days | 61-90 days | Actual cost Closure |  | FALSE | Chayan Bhattacharya | PMO | #N/A | 2026-07-13 | 53 | 11-20 Days |  | LCF-1484
FIN-6022 |  |  | CR |  |  | Change in IPB Computation Logic Flat rate on product & PPT, with Reference to JIRA ticket NO - FIN-4599 |  | Abhijay Pawar | 2026-05-07 | 2026-08-26 |  | 2026-08-31 |  | 111 | >21 Days | 91-120 days | Testing Showstopper | Vikas Chavan | TRUE | Vikas Chavan | PAS | Siddharth Godbole | 2026-06-11 | 85 | >21 Days | OPen defects to be resolved | FIN-6363, 6445, 6461, 6548
ITP-3376 |  |  | CR |  |  | CRT CCM Communication for NGIN polices(ops-1070) |  | Rahul Kumar | 2026-05-14 |  |  |  |  | 113 | >21 Days | 91-120 days | UAT | Rahul Kumar | TRUE | Rahul Kumar | UAT | Rohan | 2026-06-08 | 88 | >21 Days
ITP-5420 |  |  | CR |  |  | Enabling AA in application tracker for NGIN applications |  | sahil vathare | 2026-05-14 |  |  |  |  | 113 | >21 Days | 91-120 days | Testing Showstopper | PAS.LingamalluSaiTej | TRUE | PAS.LingamalluSaiTej | PAS | Siddharth Godbole | 2026-05-20 | 107 | >21 Days | Open defects to be resolved | AN-1638
FIN-5538 |  |  | CR |  |  | SBI OTC collections - OSB related development and integration required (non pas related) |  | Abhijay Pawar | 2026-05-15 | 2026-08-26 |  | 2026-08-31 |  | 103 | >21 Days | 91-120 days | UAT In progress | Ganesh Potawale | TRUE | Ganesh Potawale | UAT | Rohan | 2026-08-13 | 22 | 0-10 Days | Call to be closed. Tracked under main call FIN-5197
AP-2602 |  |  | CR |  |  | NRI Address change to be updated in System when will update Residential status (RI to NRI or NRI to RI) for NGIN policies (Call-OPS-16206 for OPUS) |  | Sunil Bhalerao | 2026-05-16 | 2026-09-08 |  | 2026-09-10 |  | 111 | >21 Days | 91-120 days | UAT Defect Fixing in Progress | Abhijeet Kharat | TRUE | Abhijeet Kharat | LACP | Soniel | 2026-07-14 | 52 | >21 Days | Address is updated but country is not upadated correctly
ITP-5273 |  |  | CR |  |  | NGIN Date Management Changes |  | Aditya Kumar | 2026-05-21 |  |  |  |  | 106 | >21 Days | 91-120 days | BA-TL Review | Poulami Sarkar | TRUE | Poulami Sarkar | AGILIC PMO | Vikesh S | 2026-05-27 | 100 | >21 Days
OPS-30842 |  |  | CR |  |  | Medical Grids for Savings and Investment Plans. |  | Sandip Patil | 2026-05-22 |  | 2026-07-02 |  |  | 41 | >21 Days | 31-60 days | Testing Showstopper |  | FALSE | Mukesh Bhatt | PAS | Siddharth Godbole | 2026-08-14 | 21 | 0-10 Days | Shared for signoff to NB on 1 jul 26. Feedback given to test scenarios in all live products. OPen defects to be resolved | OPS-34016, 34263, 34807, 34833, 34841, 34896, 34897
OPS-31328 | OPS-28826 |  | CR |  |  | NRI E-touch 25 cr SA Capping |  | Vaishavik Sapkal | 2026-06-01 |  |  |  |  | 95 | >21 Days | 91-120 days | Testing Showstopper | PAS.GollaNarayana | TRUE | PAS.GollaNarayana | PAS | Siddharth Godbole | 2026-07-14 | 52 | >21 Days | 20 cr already tested in E-touch product. This call raised for 25 CR SA .UAT team can’t be tested beacuse of the BI validation error of 20 CR.
ITP-4069 |  |  | CR |  |  | EKYC Document Push to Omni |  | Sunil Bhalerao | 2026-06-01 | 2026-06-05 | 2026-06-05 |  |  | 4 | 0-10 Days | 2-5 days | Actual cost Closure |  | FALSE | Chayan Bhattacharya | PMO | #N/A | 2026-06-05 | 91 | >21 Days | As per the BA comment mentioned in the parent call SIT,UAT is not possible for this requirement
BD-2390 |  |  | CR |  |  | FLC communication |  | Rahul Kumar | 2026-06-02 |  |  |  |  | 94 | >21 Days | 91-120 days | Testing Showstopper | Adityas.Patil | TRUE | Adityas.Patil | PSF | Nidhi Jain | 2026-07-27 | 39 | >21 Days
ITP-4432 |  |  | CR |  |  | DIGI: NGIN (EDC) |  | Sunil Bhalerao | 2026-06-03 | 2026-08-28 |  | 2026-09-01 |  | 93 | >21 Days | 91-120 days | Testing Showstopper | shahaji shankarrao jadhav | FALSE | Nikhilesh.Sundaresan | Analytics | Nikhilesh S | 2026-08-20 | 15 | 0-10 Days | EDC hit is available or not take a confirmation from dev team
OPS-30878 |  |  | CR |  |  | Penal Interest Logic to be built for ACE product |  | Abhijay Pawar | 2026-06-03 |  | 2026-06-30 |  |  | 27 | >21 Days | 16-30 days | Development |  | FALSE | Saloni Jain | PAS | Siddharth Godbole | 2026-07-01 | 65 | >21 Days | Awaiting development ETA confirmation
OPS-27339 |  |  | CR |  |  | PAS - Geographical loading to be mapped to special loading in IONE |  | Sandip Subhash Darade | 2026-06-10 |  | 2026-07-01 |  |  | 21 | >21 Days | 16-30 days | Testing Showstopper |  | FALSE | Mukesh Bhatt | PAS | Kalyan Patnaik | 2026-08-10 | 25 | 0-10 Days | 10-Aug-26: Additional cases shared on 10th Aug '26
Pass cases shared for signoff on 01 jul 26 to NB. Discussion to be held on 21 jul 26 on defect OPS-34367.
PD-1507 |  |  | Production Defect |  |  | Deposit bank code & GL is not getting populated in payments_dtls_table |  | Abhijay Pawar | 2026-06-11 | 2026-08-26 |  | 2026-08-31 |  | 85 | >21 Days | 61-90 days | Dev TL | PAS.AmitabhTripathi | TRUE | PAS.AmitabhTripathi | PAS | Siddharth Godbole | 2026-08-06 | 29 | 11-20 Days | Pending with PAS.Amitabh for issue resolution
OPS-27186 |  |  | CR |  |  | The buffer days for claims decision payout should be reduced from 3 days to 1 day--NGIN |  | Ankita Pawar | 2026-06-26 |  |  |  |  | 70 | >21 Days | 61-90 days | Need Business Clarification | Ajay Yadav | FALSE | balic_finance_agilicprojects | PAS | Siddharth Godbole | 2026-08-20 | 15 | 0-10 Days | Awaiting clarification from finance on query raised by PAS.TDS is cut on penal interest amount of Rs. 10000/- and above
OPS-32678 |  |  | CR |  |  | Auto PPQC Script _ NGIN Cases |  | Sandip Subhash Darade | 2026-07-07 | 2026-09-04 |  | 2026-09-07 |  | 59 | 11-20 Days | 31-60 days | Testing Showstopper | Mihir Chaudhari | TRUE | Mihir Chaudhari | CRM | Soniel | 2026-07-29 | 37 | 11-20 Days | Open defects to be resolved
OPS-33288 |  |  | CR |  |  | Residential status change |  | Sunil Bhalerao | 2026-07-08 | 2026-09-08 |  | 2026-09-10 |  | 58 | 11-20 Days | 31-60 days | UAT | deepak chajlan | FALSE | Rahul Madhukar Sasamkar | PAS | Siddharth Godbole | 2026-07-02 | 64 | >21 Days | Under defect
OPS-26867 |  |  | CR |  |  | IONE Changes-Simultaneous Policy |  | Chaitanya Shashank Kulkarni | 2026-07-08 | 2026-08-27 |  | 2026-08-27 |  | 58 | 11-20 Days | 31-60 days | Development | Avish Bhargav Kolusu | FALSE | Gaurav Arora | 0 | #N/A | 2026-07-08 | 58 | 11-20 Days | Under Development
OPS-32828 |  |  | CR |  |  | Tolerance Adjustment for Premium Collection NGIN |  | Jayaraman S | 2026-07-17 |  |  |  |  | 49 | 0-10 Days | 31-60 days | DEV TL Review | Ganesh Chandvilkar | FALSE | Mukesh Bhatt | PAS | Siddharth Godbole | 2026-08-06 | 29 | 0-10 Days
PD-2425 |  |  | Production Defect |  |  | DC details to be used for PS refund and CFI. |  | Sunil Bhalerao | 2026-07-17 | 2026-08-30 |  | 2026-09-01 |  | 49 | 0-10 Days | 31-60 days | Business Approval/Sign off | Mantesh Byali | FALSE | PAS.AmitabhTripathi | PAS | Siddharth Godbole | 2026-08-05 | 30 | 0-10 Days | Dev clarification required
OPS-33773 |  |  | CR |  |  | OSB changes - NGIN Aggregator - Allow Payment Despite Scheduled Auto Debit |  | Sunil Bhalerao | 2026-07-17 | 2026-09-10 |  | 2026-09-02 |  | 49 | 0-10 Days | 31-60 days | Testing Showstopper | Rushikesh More | TRUE | Rushikesh More | PAS | Siddharth Godbole | 2026-08-02 | 33 | 0-10 Days | Open defects to be resolved | OPS-34928
ITP-6238 |  |  | CR |  |  | APR II- Rider Variant Selection Validation – Restrict Mixing of ROP and Non-ROP Variants |  | Sathya Kumar | 2026-07-21 |  | 2026-07-22 |  | 2026-07-22 | 1 | 0-10 Days | 0-1 days | Actual cost Closure |  |  | Chayan Bhattacharya | PMO | #N/A | 2026-07-22 | 44 | 0-10 Days
BD-2715 |  |  | CR |  |  | Digital KYC Flags on BSO Screen |  | Sandip Subhash Darade | 2026-07-22 | 2026-09-01 |  | 2026-09-04 |  | 44 | 0-10 Days | 31-60 days | UAT In progress | Sandip Subhash Darade | TRUE | Sandip Subhash Darade | UAT | Rohan | 2026-08-04 | 31 | 0-10 Days | Awaiting BSO point to be change from Prashant Thanekar
FIN-6055 |  | Preprod | CR |  |  | Required role updation in PMACS |  | Abhijay.Pawar01 | 2026-07-28 | 2026-08-26 |  | 2026-08-31 |  | 29 | 0-10 Days | 16-30 days | Pending for Sign-Off | Abhijay.Pawar01 | FALSE | balic_finance_agilicprojects | PAS | Siddharth Godbole | 2026-07-28 | 38 | 0-10 Days | Cases Shared for review pending for sign off
ITP-6127 |  |  | CR |  |  | OTP (Customer and SP )Stamping on PF- Audit and compliance requirement |  | chaitanya shashank kulkarni | 2026-07-28 | 2026-08-20 | 2026-08-24 | 2026-08-24 |  | 27 | 0-10 Days | 16-30 days | Actual cost Closure | Chayan Bhattacharya | TRUE | Chayan Bhattacharya | PMO | #N/A | 2026-08-24 | 11 | 0-10 Days
AG-6967 |  |  | CR |  |  | New GST Login in Agency Commission Processing |  | Nilesh Sawant | 2026-07-27 |  | 2026-07-29 |  | 2026-07-29 | 2 | 0-10 Days | 2-5 days | Actual cost Closure | Chayan Bhattacharya | TRUE | Chayan Bhattacharya | PMO | #N/A | 2026-08-03 | 32 | 0-10 Days
FIN-4579 |  |  | CR |  |  | GL batch related control reports |  | Abhijay Pawar | 2026-07-29 | 2026-08-26 |  | 2026-08-31 |  | 37 | 0-10 Days | 31-60 days | Development | Sohan Lal Maurya | TRUE | Sohan Lal Maurya | PAS | Siddharth Godbole | 2026-07-30 | 36 | 0-10 Days | demo is pending from infy
ITP-5931 |  |  | CR |  |  | RHSSO URL Changes for upgrade to RHBK |  | Abhijay Pawar | 2026-07-31 | 2026-08-26 |  | 2026-08-31 |  | 35 | 0-10 Days | 31-60 days | Pre-Prod In Progress | Kunjan.Pamani | TRUE | Kunjan.Pamani | Jira PMO | Chayan Bhattacharya | 2026-08-07 | 28 | 0-10 Days
AN-1649 |  |  | CR |  |  | Auto‑merge CP IDs based on ECI API response (NGIN) |  | Sandip Subhash Darade | 2026-08-04 | 2026-08-31 |  | 2026-08-31 |  | 31 | 0-10 Days | 31-60 days | UAT In progress | Sandip Subhash Darade | TRUE | Sandip Subhash Darade | UAT | Rohan | 2026-08-04 | 31 | 0-10 Days | UAT WIP
OPS-32679 |  |  | CR |  |  | PAS - Revised BI Functionality in NGIN QC |  | Vaishavik sapkal | 2026-08-10 | 2026-08-26 |  | 2026-08-31 |  | 25 | 0-10 Days | 16-30 days | Development | Vaishavik sapkal | FALSE | Mahesh Dahale | PAS | Siddharth Godbole | 2026-08-11 | 24 | 0-10 Days
PD-2194 |  |  | Production Defect |  |  | NGIN Payout Module in Frontend screen add Cheque Number |  | Harshal Chougule | 2026-08-11 |  | 2026-08-12 |  |  | 1 | 0-10 Days | 0-1 days | Business Approval/Sign off | Harshal Chougule | FALSE | PAS.AmitabhTripathi | PAS | Siddharth Godbole | 2026-08-11 | 24 | 0-10 Days | Awaiting for signoff
ITP-6368 |  |  | CR |  |  | Digi-related changes in ACE Advantage |  | Aditya Kumar | 2026-08-13 | 2026-08-26 |  | 2026-08-31 |  | 22 | 0-10 Days | 16-30 days | UAT In progress | Rohini Baburao Gurme | TRUE | Rohini Baburao Gurme | UAT | Rohan | 2026-08-13 | 22 | 0-10 Days
PD-726 |  |  | Production Defect |  |  | Duplicate Entry for the medical test changes API |  | Manmath Umbare | 2026-08-10 | 2026-08-26 |  | 2026-08-31 |  | 25 | 0-10 Days | 16-30 days | UAT In progress | Manmath Umbare | TRUE | Manmath Umbare | UAT | Rohan | 2026-08-10 | 25 | 0-10 Days | UAT In progress
FIN-6437 |  | Preprod | CR |  |  | With reference to old call (FIN-4028) Incorrect loss/gain code in CDA reversal accounting |  | Abhijay Pawar | 2026-06-12 | 2026-08-26 |  | 2026-08-31 |  | 84 | 0-10 Days | 61-90 days | Testing Showstopper | Sohan Lal Maurya | TRUE | Sohan Lal Maurya | PAS | Siddharth Godbole | 2026-08-17 | 18 | 0-10 Days
OPS-28978 |  |  | CR |  |  | SR categories in CRM which requires integration in NGIN |  | Sunil Bhalerao | 2026-08-19 | 2026-09-05 |  | 2026-03-09 |  | 16 | 0-10 Days | 16-30 days | UAT In progress | Sunil Bhalerao | TRUE | Sunil Bhalerao | UAT | Rohan | 2026-08-19 | 16 | 0-10 Days | UAT In progress
BD-2385 |  |  | CR |  |  | Onboard IPPB Non-Integrated on NGIN platform |  | Winston Roy | 2026-08-21 | 2026-08-29 |  | 8/31/2026 |  | 14 | 0-10 Days | 9-15 days | Testing Showstopper | Rahul Dhokane | FALSE | Anirudh Nair | DIGI | Prakash Swain | 2026-08-21 | 14 | 0-10 Days | UAT In progress
OPS-30905 |  |  | CR |  |  | Freelook Payouts Enhancement in NGIN |  | Ganesh Pawar | 2026-08-24 | 2026-09-04 |  | 2026-09-07 |  | 11 | 0-10 Days | 9-15 days | UAT In progress | Ganesh Pawar |  | Ganesh Pawar | UAT | Rohan | 2026-08-24 | 11 | 0-10 Days | UAT In progress
FIN-6433 |  |  | CR |  |  | Clearance updation in NGIN |  | Harshal Chougule | 2026-08-24 | 2026-09-04 |  | 2026-09-07 |  | 11 | 0-10 Days | 9-15 days | Testing Showstopper | Abhijay.Pawar01 |  | balic_finance_agilicprojects | PAS | Siddharth Godbole | 2026-08-25 | 10 | 0-10 Days | Testing Showstopper
PD-2514 |  |  | Production Defect |  |  | Premium adjustment not getting reversed on CDA/Receipt cancellation |  | Harshal Chougule | 2026-08-26 | 2026-09-05 |  | 2026-09-08 |  | 9 | 0-10 Days | 9-15 days | UAT TL Review | balic_finance_agilicprojects |  | balic_finance_agilicprojects | PAS | Siddharth Godbole | 2026-09-02 | 2 | 0-10 Days | UAT TL Review
OPS-30040 |  |  | CR |  |  | API Integration for Urban/Rural Classification Based on Pin Code |  | Sandip Subhash Darade | 2026-08-27 | 2026-09-05 |  | 2026-09-08 |  | 8 | 0-10 Days | 6-8 days | Pre-Prod In Progress | Sandip Subhash Darade |  | Sandip Subhash Darade | UAT | Rohan | 2026-08-27 | 8 | 0-10 Days | UAT In progress
PD-2537 |  |  | Production Defect |  |  | Incorrect PPD Date Displayed in NGIN Due List |  | Mayuri Tetwar | 2026-09-02 | 2026-09-10 |  | 2026-09-14 |  | 2 | 0-10 Days | 2-5 days | UAT In progress | Sunil Bhalerao |  | Sunil Bhalerao | UAT | Rohan | 2026-09-02 | 2 | 0-10 Days | UAT In progress
OPS-30089 |  |  | CR |  |  | Revamping Fund Value statement |  | Sunil Bhalerao | 2026-08-20 | 2026-09-17 |  |  |  | 15 | 0-10 Days | 9-15 days | Testing Show Stopper | Vikas Chavan |  | Vikas Chavan | PAS | Siddharth Godbole | 2026-09-02 | 2 | 0-10 Days | Testing Show Stopper
OPS-29734 |  |  | CR |  |  | Split payment for NGIN payout of NB rejection |  | Pranit Sasane | 2026-09-02 | 2026-09-11 |  | 2026-09-14 |  | 2 | 0-10 Days | 2-5 days | UAT In progress | Pranit Sasane |  | Pranit Sasane | UAT | Rohan | 2026-09-02 | 2 | 0-10 Days | UAT In progress
PD-2536 |  |  | CR |  |  | Duplicate Policy Records Extracted in NGIN Due List |  | Nikesh Maske | 2026-09-03 | 2026-09-13 |  | 2026-09-18 |  | 1 | 0-10 Days | 0-1 days | UAT In progress | Nikesh Maske |  | Nikesh Maske | UAT | Rohan | 2026-09-03 | 1 | 0-10 Days | UAT In progress